## Resource Sheet
Resource Sheet
Resource Name | Monthly Cost | Estimated Months | Estimated Hours | Hourly Rate (PKR) | Total Cost (PKR)
Project Manager | 40000 | 6 | 96 hrs | 2,000/hr | 240000
UI/UX Designer | 60000 | 6 | 72 hrs | 1,800/hr | 360000
Frontend Developer | 108000 | 4 | 128 hrs | 3,375/hr | 432000
Backend Developer | 120000 | 4 (Oct–Jan + Mar) | 132 hrs | 3,333/hr | 440000
Database Administrator | 54000 | 3 | 84 hrs | 1,885/hr | 158000
QA Tester | 60000 | 4 | 120 hrs | 1,833/hr | 220000
DevOps Engineer | 40000 | 3 | 72 hrs | 2,222/hr | 100000
Trainer/Support Officer | 18000 | 2 | 16 hrs | 1,688/hr | 27000
Software Deployment | 10000 | 6 (fixed/monthly) | — | — | 60000
Cloud Hosting | 60000 | 1 (March only) | — | — | 60000
Reserves (20%) | — | — | — | — | 433200
DBA Overhead (30%) | — | — | — | — | 47400

## Cost Sheet
Cost Sheet (PKR)
Role | Monthly Cost | October,2025 | November,2025 | December,2025 | January,2026 | February,2026 | March,2026 | Total Cost
Project Manager | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 240000
UI/UX Designer | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 360000
Frontend Developer | 108000 | 108000 | 108000 | 108000 | 80000 | 0 | 0 | 404000
Backend Developer | 120000 | 120000 | 120000 | 120000 | 40000 | 0 | 40000 | 440000
Database Administrator | 54000 | 54000 | 54000 | 30000 | 20000 | 0 | 0 | 158000
QA Tester | 60000 | 0 | 0 | 40000 | 60000 | 60000 | 60000 | 220000
DevOps Engineer | 40000 | 0 | 0 | 0 | 40000 | 40000 | 20000 | 100000
Trainer/Support Officer | 18000 | 0 | 0 | 0 | 0 | 9000 | 18000 | 27000
Software Deployment | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 60000
Cloud Hosting Service | 60000 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000
20% of All Estimate | — | 78400 | 78400 | 81600 | 70000 | 43800 | 61600 | 413800
30% of DBA (Overhead) | — | 16200 | 16200 | 9000 | 6000 | 0 | 0 | 47400
Total/Month | — | 486600 | 486600 | 498600 | 426000 | 262800 | 369600 | 2530200
Note: It’s 85–90% aligned with your plan structure and task durations, but not 100% accurate in monthly cost distribution per resource because we didn't break down hours day-by-day.

## Budget Summary
Budget Summary – University Societies Management System
Summary Sheet
Project Element | Details
Project Start Date | 2025-10-17
Project End Date | 2026-04-17
Total Duration | 6 months
Total Tasks | 53
Key Milestones | Requirements Sign-Off (Jan 1, 2026), Final Deployment (Apr 9, 2026)
Total Work Hours | 1000+
Estimated Budget | ≈ PKR 3.1 Million
Assigned Resources | 20+ team members
Critical Path Tasks | DB Dev → Modules → Integration → Deployment